## Timeline draft
|  |  | 2018 | [8 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
M Management Leader: BRHCA |  | Deliverable
1 | Kick off meeting Finland | Memo | [36 empty] | Kick off meeting together with HEAT training | bar: 2018 4 to 2018 6
2 | Project team meeting 2 Sweden | Memo | [36 empty] | Together with study visit and seminar | bar: 2018 9 to 2018 10
3 | Project team meeting 3 Latvia | Memo | [36 empty] | Together with sum up of the planning for workshops and HEAT analysis | bar: 2019 4 to 2019 5
4 | Project team meeting 4 Estonia | Memo | [36 empty] | Togther with conclusion on results from workshops and project workshop on campaigning | bar: 2019 9 to 2019 10
5 | Project team meeting 5 Finland | Memo | [36 empty] | Mid-term review of the actions in the cities | bar: 2020 4 to 2020 5
6 | Final project team meeting Finland | Memo | [36 empty] | Together with final seminar | bar: 2020 11 to 2020 12
7 | Project team meetings online | Memos (2x6) | bar: 2018 4; 2018 7; 2018 10; 2019 1; 2019 4; 2019 7; 2019 9; 2019 12; 2020 3; 2020 6; 2020 9; 2020 12
8 | SG meeting | Memo (6) | bar: 2018 4; 2018 12; 2019 5; 2019 12; 2020 5; 2020 11
9 | Reporting | Reports (6+1) | bar: 2018 10; 2019 4; 2019 10; 2020 4; 2020 12
T1 Interactive workshops Leader: Valonia |  | Deliverable
1 | Study visit to Sweden - citizen participation | Agenda, report, article on the website | [36 empty] | Activty 1 and 2 together | bar: 2018 9 to 2018 10
2 | Seminar on citizen participation | Programme, presentation, article on the website | bar: 2018 9 to 2018 10
3 | Review of the games and other tools to be used during planning workshops for citizens | Report | bar: 2018 4 to 2018 7
4 | Development/adaptation of the game and other tools for planing workshops with citizens | Game or another tool for an interactive planning workshop with citizen | bar: 2018 8 to 2019 3
5 | Development of the concept of the planning workshop for citizens | Concept | bar: 2018 10 to 2018 12
6 | Planning of the planning workshop for citizens in each city | Plan | bar: 2019 1 to 2019 3
7 | Interactive planning workshops for citizens in each city | Programme, reports, articles in the newspapers | bar: 2019 4 to 2019 9
8 | Conclusion on the results - seminar in Estonia | Report, article on the website | bar: 2019 9 to 2019 10
9 | Webinar on participatory urban planning | Presentation | [36 empty] | Moved to WP Communication | bar: 2019 9 to 2019 10
10 | Development of guidebook for urban planners on citizens participation - in consultations with people and urban planners | Guidebook Ebook | [36 empty] | Final result to be presented at the final seminar | bar: 2019 4 to 2020 12
T2 Involvement of other sectors Leader: AMK |  | Deliverable
1 | Training on HEAT calculation - in Turku together with kick off | Workshop materials, website article, written plan to be used in the cities | bar: 2018 4 to 2018 6
2 | Local workshops on HEAT calculation in each city | Presentations (3+1) | bar: 2018 6 to 2018 9
3 | HEAT calculation, incl. Peer consultations between the cities | Calculation for each city | bar: 2018 8 to 2019 5
4 | Conclusion on results - seminar in Latvia: Economic arguments for healthy urban planning | Joint report, evaluation | bar: 2019 4 to 2019 5
5 | Local seminars on results | Memos 4, articles in the newspapers 3 | bar: 2019 2 to 2019 5
6 | Webinar on HEAT tool for urban planning | Presentation | [36 empty] | Moved to WP Communication | bar: 2019 4 to 2019 5
T3 Healthier urban planning Leader: Tartu City |  | Deliverable
1 | Workshop on integrated urban planning | Materials 1, articles 2 | [36 empty] | Together with conclusions of results from workshops | bar: 2019 9 to 2019 10
2 | Development of integrated concept for biking in each city | Publication 4, workshops 4 | bar: 2019 10 to 2020 9
3 | Actions in Jurmala | Jurmala plan | bar: 2019 10 to 2020 9
4 | Actions in Tartu | Tartu plan | bar: 2019 10 to 2020 9
5 | Actions in Stockholm | Stockholm plan | bar: 2019 10 to 2020 9
6 | Actions in Southwest Finland | Plan for Southwest Finland | bar: 2019 10 to 2020 9
7 | Campaigns promoting biking in each city | Materials, articles | [36 empty] | Moved to WP Communication | bar: 2020 1 to 2020 2; 2020 6 to 2020 7
8 | Local stakeholders meetings | Memos: 4 cities x2 meetings | bar: 2019 10 to 2020 9
T4 Advocacy Leader: Cykelfrämjandet |  | Deliverable
1 | Stakeholders and inititives mapping on the local and regional level | Stakeholder map | bar: 2018 7 to 2018 12
2 | Local meeting for stakeholders (3): role of citizens in the urban planning for biking , wintercycling, integerated biking initiatives. | Memos (3) | bar: 2018 12 to 2019 1; 2019 12 to 2020 1; 2020 11 to 2020 12
3 | Project workshop on campaigning during the seminar in Estonia | Materials | [36 empty] | Together with the seminar on the results from participatory workshops in Estonia | bar: 2019 9 to 2019 10
4 | Preparation of campains in the cities | Campaign materials (4) | [36 empty] | Campaigns as part of WP4, activity 6. | bar: 2019 9 to 2020 5
5 | Webinars on wintercycling and integreated biking initiatives | Presentations | [36 empty] | Moved to WP Communication | bar: 2019 12 to 2020 1; 2020 11 to 2020 12
6 | Development of local and regional policy recommendations for integrated healthy and active urban planning in the participating cities and CB region - input from the project, workshops, seminar | Website with clips | [36 empty] | This is an ongoing activity. Final result to be presented at the final seminar | bar: 2018 11 to 2020 12
8 | Establishing peer network for urban planners in the CB area | Online network | [36 empty] | Ongoing activity
WP Communication
1 | Start up activities incl.communication startegy | Communication strategy 4.2018
Project website 4.2018
2 | Publications | Articles on the following topics:
- Study visit to Sweden - Citizen Participation 10.2018
- Conclusion of results of games & workshops 10.2019
- Review of games and tools to be used 9.2018
- Economic arguments for healthy urban planning 6.2019
Launch of the guidebook E-Book for urban planners on citizen participation 12.2020
Project related articles published in the local newspapers, at least 2x location
3 | Public events | Campaigns promoting cycling in participating cities, Jan-July 2020
4 | Promotion materials | Campaign materials from each participating city, Jan-July 2020
5 | Digital activities | Webinars on the following topics:
- Participatory urban planning 10.2019
- HEAT calculation tool for urban planning 5.2019
- Winter cycling 1.2020
- Integrated biking initiatives 12.2020
Launch of interactive website with a video highlighting key policy recommendations for local and regional integrated healthy and urban planning, 12.2020
Launch of online network for urban planners in the Central Baltic area, 12.2020