## WP2-T1-Business modal
APPLICATION | MODIFICATION
Summary | Summary
The aim of the work package is to create a solid basis for the further work. Currently, there is no working business model regarding the common ticketing system between different countries that the project partnership is aware of. Thus, one has to be created. | The aim of the work package is to create a solid basis for the further work. Currently, there is no working business model regarding the common ticketing system between different countries that the project partnership is aware of. Thus, one has to be created.
The work begins with the market analysis and benchmarking to map the possible existing practices (in case there are such), bringing out their pros and cons. The work will be done by the project staff. Thus, no tendering is foreseen in this work package. | The work begins with the market analysis and benchmarking to map the possible existing practices (in case there are such), bringing out their pros and cons. The work will be done by the project staff. Thus, no tendering is foreseen in this work package.
Based on the results, different business models will be discussed. This will be done during the internal working group meetings. The meetings consist of the experts from the partner organisations in addition to project staff. Altogether, some 6 meetings will be held (once a month). The meetings are meant for discussing different possibilities on creating and monetizing the international ticketing systems. Reasearch will be done in between the meetings. | Based on the results, different business models will be discussed. This will be done during the internal working group meetings. The meetings consist of the experts from the partner organisations in addition to project staff. The meetings are meant for discussing different possibilities on creating and monetizing the international ticketing systems. Reasearch will be done in between the meetings.
In addition to internal workshops, consultations with the stakeholders (i.e. transportation companies) will be carried out. This will be done to verify the possible solutions in the real market and see, if the companies would be willing to join with the proposed system. There will be 2 meetings, but the internal working group members will consult the stakeholders throughout the process (e.g through bilateral meetings). | In addition to internal workshops, consultations with the stakeholders (i.e. transportation companies) will be carried out. This will be done to verify the possible solutions in the real market and see, if the companies would be willing to join with the proposed system. There will be 2 meetings, but the internal working group members will consult the stakeholders throughout the process (e.g through bilateral meetings).
The leadership of the work package belongs to HSL due to the Finns' extensive knowledge in involving stakeholders and facilitating the processes of the kind. | The leadership of the work package belongs to HSL due to the Finns' extensive knowledge in involving stakeholders and facilitating the processes of the kind.
The process will take approximately 8 months in total, but it is planned that some work of the other work packages (developing) can start in parallel. | The process will take approximately 4 months in total, but it is planned that some work of the other work packages (developing) can start in parallel.
Project output O.T1.1 | Project output O.T1.1
A thoroughly discussed document indicating clearly the business principles of an international ticketing system. The model also serves as the showcase for the other regions in Europe. | A thoroughly discussed document indicating clearly the business principles of an international ticketing system. The model also serves as the showcase for the other regions in Europe.
The business model at least describes the following: similar solutions elsewhere in the world, value added to the end-users, partnership composition, sales and marketing, revenues (incl. sharing) and costs. | The business model at least describes the following: similar solutions elsewhere in the world, value added to the end-users, partnership composition, sales and marketing, revenues (incl. sharing) and costs.
Programme output indicator of chosen specific objective | Programme output indicator of chosen specific objective
Number of developed and improved transport corridors and nodes | Helsinki-Tallinna-Tarto possibilty to expand to other cities and countries
Deadline: December 2018 | Deadline: February 2019
WP target groups | WP target groups
local public authority | local public authority
national public authority | national public authority
infrastructure and (public) service provider | infrastructure and (public) service provider
enterprise, excluding SME | enterprise, excluding SME
SME | SME
General public | General public
The model describes the role of the different parties (national and local public authorities, enterprises etc.) related to common ticketing system. Basically, the model creates a comprehensive picture of the system, clearly bringing out the added value for the end-user (general public). During the process, mostly enterprises, including the SMEs will be consulted. Also, the working groups themselves consist of the representatives of the public authorities. | The model describes the role of the different parties (national and local public authorities, enterprises etc.) related to integrated ticketing systems. Basically, the model creates a comprehensive picture of the system, clearly bringing out the added value for the end-user (general public). During the process, mostly enterprises, including the SMEs will be consulted. Also, the working groups themselves consist of the representatives of the public authorities.
There are also communication activities foreseen to inform the general public - how the model would work, if and how it would influence the daily travellers etc (i.e. press release). These activities are described under the relevant work package (communication).
Durability and transferability of main outputs | Durability and transferability of main outputs
The business model will be designed to be applicable (or adjustable) for the other regions to take Estonia and Finland as a good example. Thus, the work package is relevant not only for the very project, but also for the wider spectrum | The business model will be designed to be applicable (or adjustable) for the other regions to take Estonia and Finland as a good example. Thus, the work package is relevant not only for the very project, but also for the wider spectrum. Clearing to be always discussed locally
The business model will act as a basis for further development. The big idea is not to stick only with a few ticket products, but to change the whole ecosystem. So, based on the principles worked out during this project, new developments can be built upon. The ownership of the model will be taken by the project partners, who will commit themselves to further development after the project has ended. | The business model will act as a basis for further development. So, based on the principles worked out during this project, new developments can be built upon. The ownership of the model will be taken by the project partners, who will commit themselves to further development after the project has ended.
Activity A.T1.1 | Activity A.T1.1
Market analysis and benchmarking, if possible | Market analysis and benchmarking, if possible
Period: May-August 2018 | Period: May-December 2018
Deliverable D.T1.1.1: Market analysis (a document) that describes the possible ticketing solutions | Deliverable D.T1.1.1: Market analysis (a document) that describes the possible ticketing solutions
Activity A.T1.2 | Activity A.T1.2
Internal working groups (6 meetings in total) | Internal working groups (3 meetings in total)
Period: July-October 2018 | Period: September 2018-February 2019
Deliverable D.T1.2.1: Meeting minutes, including business principles (6) | Deliverable D.T1.2.1: Meeting minutes, including business principles (3)
Deliverable D.T1.2.2: Agreed and documented business model | Deliverable D.T1.2.2: Agreed and documented business model
Activity A.T1.3 | Activity A.T1.3
External workshops (2 meetings in total, additionally 1-on-1 consultations) | External workshops (2 meetings in total, additionally 1-on-1 consultations)
Period: August-December 2018 | Period: August-February 2019
Deliverable D.T1.3.1: Meeting minutes, including pilot agreements (i.e. companies, who will join the development of the common ticket product) (2) | Deliverable D.T1.3.1: Meeting minutes, including pilot agreements (i.e. companies, who will join the development of the common ticket product) (2)

## WP3-T2-Developing and testing
APPLICATION | MODIFICATION
Summary | Summary
The working package forms the core of the project. It aims at creating a common ticketing system with a tangible result - a ticket product for the Estonian and Finnish travellers. Also, central ticketing system database will be developed. | The working package forms the core of the project. It aims at creating an integration between ticketing systems with a tangible result - a ticket products for the Estonian and Finnish travellers. Also, data synchronization interface will be developed.
Currently, the ticketing systems in Tallinn (and Tartu) and Helsinki are different. It means that in Tallinn (also in Tartu), the information is stored in the servers, while it is card-based in Helsinki. This results in non-compatability. In addition, the card standards are also different, thus, card readers in Helsinki are not able to read Estonian cards and vice versa. | Currently, the ticketing systems in Tallinn (and Tartu) and Helsinki are different. It means that in Tallinn (also in Tartu), the information is stored in the servers, while it is card-based in Helsinki. This results in non-compatability. In addition, the card standards are also different, thus, card readers in Helsinki are not able to read Estonian cards and vice versa. There are also mobile applications in all cities which allow to buy specific ticket products on mobile phones. While in Tallinn the validation of mobile ticket is obligatory using self-service validator, in Helsinki only visual validation by the driver is used. There is also possibility to use contactless bankcards (cEMV) in Tallinn public transport.
So, to solve the issues, the following activities need to be undertaken. Firstly, specifications (cards and APIs) need to be standardised. This will be done during the expert meetings (involves the IT development companies that will be outsourced). Every step will be carefully documented to be able to track the history in order to avoid possible mistakes. The standardisation process will look into the future and take the new technologies, including QR, NFC into consideration. As a result, the basis for IT development will be made during the standardisation process. | So, to solve the issues, the following activities need to be undertaken. Firstly, specifications (cards and APIs) need to be worked out. This will be done during the expert meetings (involves the IT development companies that will be outsourced). Every step will be carefully documented to be able to track the history in order to avoid possible mistakes. The process will look into the future and take the new technologies into consideration. As a result, the basis for IT development will be made during the process.
Secondly, the development according to the specifications will be carried out. This means programming and creating the APIs. Also, the minimum viable ticket selling interface (webpage) for the end-users will be created. The development also consists of testing and documentation of the whole process. | Secondly, the development according to the specifications will be carried out. This means programming and creating the APIs. Also, the minimum viable ticket selling interface for the end-users will be created. For the first stage - mobile ticket integration - it means additional development of respective mobile applications in all cities, for next stages additional development of customer portals (webpages). The development also consists of testing and documentation of the whole process.
In addition, the central ticketing database in Tartu will be developed to enable information request for different service providers. The system will be an intermediate between private companies and the municipality. | In addition, the synchrinization interfaces for tickets and cards (tokens) will be developed to enable integration between different service providers (private companies and the municipality).
The lead of the work package will be taken by City of Tallinn due to more experience in developing the online ticketing systems. | The lead of the work package will be taken by City of Tallinn due to more experience in developing the online ticketing systems.
Project output O.T2.1 - Common ticket product | Project output O.T2.1 - Interoperable ticket product
The common ticket product means that people travelling to Tallinn from Helsinki (and vice versa) do not have to purchase a new card, but can buy the online ticket to their already existing cards (Ühiskaart in Estonia and Matkakortti in Finland). | At the first stage the interoperable ticket product means that people travelling to Tallinn (or Tartu) from Helsinki (and vice versa) can buy Tallinn (and Tartu) public transport mobile ticket from Helsinki's mobile application (and vice versa). At the second stage an interoperability for contactless EMV cards will be created by integrating customer portals in a way, that customer can see its trips and payments for all cities in the same interface. At the third stage the interoperability with existing travel cards will be developed. It means that people do not have to purchase a new travel card, but can buy the online ticket to their already existing travel cards (Ühiskaart in Estonia and Matkakortti in Finland). This will be done in an account based principle, meaning that no actual ticket information will be written on the card itself, but the card will act as a token only for the systems.
The ticket product also consists of the common selling interface, where the end-users will be able to buy the tickets. | Ticket selling interfaces in all partner cities will feature additional ticket products for other cities. This allows passengers to continue buying tickets in the environment they are used to.
Project output O.T2.2 - Central ticketing system database | Project output O.T2.2 - Synchronization interfaces
Development of central technical ticketing system database to enable information requests for different service providers (transportation providers). This system will be the intermediate between private companies, who need to request information and public organisations who own data. The database will be open for joining for public organisations, e.g. local municipalities, governmental organisations etc. It is a needed link to increase the comfort for travellers and equalise the conditions of competition between service providers in Estonia. It also consist analyses and modelling the rules for joining new users and principles of action, which is basically a business model to manage the database. | Development of the synchronization interfaces for tickets and cards (tokens) to enable integration between different service providers (private companies and the municipality). Interface specifications will be open for all interested parties. It also consist analyses and modelling the rules for joining new users and principles of action, which is basically a business model to manage the future integrations.
Programme output indicator of chosen specific objectives | Programme output indicator of chosen specific objectives
Number of developed and improved transport corridors and nodes | Number of developed and improved transport corridors and nodes
Deadline: May 2020 | Deadline: December 2020
WP target groups | WP target groups
no changes planned
Durability and transferability of main outputs | Durability and transferability of main outputs
The common ticket product is a proof of concept to show that the business model works. The result can be indirectly used by other regions. However, the system needs to be adapted to their needs and realities. | The interoperable ticket products is a proof of concept to show that the business model works. The result can be indirectly used by other regions. However, the system needs to be adapted to their needs and realities.
The ticket product will remain in public use after the end of the project. In addition, there will be more products developed based on the gained knowledge and agreed specifications. | The ticket products will remain in public use after the end of the project. In addition, there will be more products developed based on the gained knowledge and agreed specifications.
Activity A.T2.1 | Activity A.T2.1
Standardising specifications (i.e. card platforms, APIs etc.) | Agreeing specifications and APIs for interoperable mobile tickets
Period: December 2018 - July 2019 | Period: December 2018 - July 2019
Deliverable D.T2.1.1: Report: clearing system, agreed specifications that form the basis for development | Deliverable D.T2.1.1: Report: clearing principles, agreed specifications that form the basis for development
Activity A.T2.2 | Activity A.T2.2
Developing the ticketing system in Tallinn and Tartu, incl. testing | Tendering procedures for finding the IT developers (Mobile ticketing)
Perion: June 2019 - May 2020 | Period: January - March 2019
Deliverable D.T2.2.1: Modified ticket system that is compatible with Finnish, incl. thorough documentation about the process. There are probably fewer changes necessary than in Helsinki as the system is already cloud-based. | Deliverable D.T2.2.1: Contract with the IT developer in Tallinn and Tartu to adjust the system and make it compatible with Helsinki
Activity A.T2.3
Tendering procedures for finding the IT developers | Activity A.T2.3
Period: November 2018 - February 2019 | Developing mobile applications for enabling interoperable mobile ticketing products in Tallinn, Helsinki and Tartu. incl. testing
Deliverable D.T2.3.1: Contract with the IT developer in Tallinn to adjust the system and make it compatible with Helsinki | Period: July 2019 - February 2020
Deliverable D.T2.3.2: Contract with the IT developer in Helsinki to renew/rebuild the system and make it compatible with Tallinn | Deliverable D.T2.3.1: Prototype level mobile application (end October 2019), target value 2
Deliverable D.T2.3.2: Production quality mobile application target value 2
Deliverable D.T2.3.3: Contract with the IT developer in Tartu to build the central ticketing system database
Activity A.T2.4
Activity A.T2.4 | Tendering procedures for finding the IT developers (EMV ticketing)
Developing the central ticketing system database, incl. testing | Period: February-August 2019
Period: December 2018 - May 2020 | Deliverable D.T2.4.1: Contract with the IT developer in Tallinn and Tartu to adjust the system and make it compatible with Helsinki
Deliverable D.T2.4.1: Analysis and rules for the joining new users (i.e. business model for managing the database) | Deliverable D.T2.4.2: Contract with the IT developer in Helsinki to create the system and make it compatible with Tallinn and Tartu (cEMV and PSP procurement HSL)
Deliverable D.T2.4.2: Central ticketing system database in Tartu, which architecture is usable in other municipalities
Activity A.T2.5
Activity A.T2.5 | Tendering procedures for finding the IT developers (ID-based ticketing)
Developing minimum viable ticket selling interface (i.e. platform, where users can purchase tickets), incl. testing | Period: February-September 2019
Period: June 2019 - May 2020 | Deliverable D.T2.5.1: Contract with the IT developer in Tallinn and Tartu to adjust the system and make it compatible with Helsinki
Deliverable D.T2.5.1: Minimum viable ticket selling interface | Deliverable D.T2.5.2: Contract with the IT developer in Helsinki to create the system and make it compatible with Tallinn and Tartu (ID based back end system procurement HSL)
Activity A.T2.6 | Activity A.T2.6
Developing the ticketing system in Helsinki, incl. testing | Agreeing specifications and APIs for interoperable travel and payment history for contactless EMV cards
Period: June 2019 - May 2020 | Period: September 2019 - February 2020
Deliverable D.T2.6.1: Modified ticket system that is compatible with Estonian, incl. thorough documentation about the process | Deliverable D.T2.6.1: Agreed specifications that form the basis for development
Activity A.T2.7
Agreeing specifications and API-s for synchronization interfaces for tickets and cards (tokens)
Period: September 2019 - February 2020
Deliverable D.T2.7.1: Agreed specifications that form the basis for development
Activity A.T2.8
Developing interoperable PCI-DSS compliant customer interfaces for contactless EMV card travel and payment history for Tallinn, Helsinki and Tartu. incl. testing
Period: February 2020 - July 2020
Deliverable D.T2.8.1: Minimum viable PCI-DSS compliant contactless EMV card travel and payment history interfaces (customer portals) for all cities.
Activity A.T2.9
Development of the synchronization interfaces for tickets and cards (tokens)
Period: July 2020 - November 2020
Deliverable D.T2.9.1: Analysis and rules for the joining new users, principles of actions (i.e. business model for managing the future integrations)
Activity A.T2.10
Developing the interoperability of travel cards on account based principle, incl. testing
Period: June 2020 - December 2020
Deliverable D.T2.10.1: Travel cards are interoperable (Ühiskaart works in Helsinki and Matkakortti works in Tallinn and Tartu).
Activity A.T2.11
Internal working groups (6 meetings in total)
Period: February 2019 - January 2021
Deliverable D.T1.2.1: Meeting minutes, including developing principles (3)

## WP4-T3-Piloting
APPLICATION | MODIFICATION
Summary | Summary
The aim of the work package is to pilot the common ticket product in real life. The product has been tested during the previous work package, but there is no feedback from the end-customers. | The aim of the work package is to pilot the interoperable ticket products in real life. The products have been tested during the previous work package, but there is no feedback from the end-customers.
The activities start with the closed pilot. This means that there will be an open call for the citizens to take part in the testing. Those interested will be registered and their feedback will systematically be collected. According to the feedback, adjustments in the system, including the ticket selling application will be made. There will be at least 200 test-users involved. | The activities start with the closed pilot. This means that there will be an open call for the citizens to take part in the testing. Those interested will be registered and their feedback will systematically be collected. According to the feedback, adjustments in the system, including the ticket selling application will be made. There will be at least 200 test-users involved.
Depending on the feedback, the project consortium may decide to open the product up for everybody even before the end of the project. The pre-condition is that the ticket product has received mostly positive feedback from the end-users and the adjustments that need to be done are rather minor. | Depending on the feedback, the project consortium may decide to open the product up for everybody even before the end of the project. The pre-condition is that the ticket products have received mostly positive feedback from the end-users and the adjustments that need to be done are rather minor.
In case there is more work to be done, the ticket product will be openly announced in the end of the project. | In case there is more work to be done, the ticket products will be openly announced in the end of the project.
Project output O.T3.1: Tested common ticket product | Project output O.T3.1: Tested interoperable mobile ticket sale channel
The common ticket product has been publicly tested and feedback received. As a result, it is fully usable and shortens the time spent on travelling. | The interoperable mobile ticket sale channel has been publicly tested and feedback received. As a result, it is fully usable and shortens the time spent on travelling.
Programme output indicator of chosen specific objective | Project output O.T3.2: Tested interoperable payment options with EMV and travel cards
Number of developed and improved transport corridors and nodes | The interoperable payment options with EMV and travel cards have been publicly tested and feedback received. As a result, it is fully usable and shortens the time spent on travelling.
Deadline: April 2021
Programme output indicator of chosen specific objective
Number of developed and improved transport corridors and nodes
Deadline: April 2021
WP target groups | WP target groups
local public authority | local public authority
national public authority | national public authority
infrastructure and (public) service provider | infrastructure and (public) service provider
enterprise, excluding SME | enterprise, excluding SME
SME | SME
General public | General public
The main emphasis is put on the end-users - travellers. The feedback from them will carefully be analysed and taken into consideration. According to that, adjustments in the product will be made. | The main emphasis is put on the end-users - travellers. The feedback from them will carefully be analysed and taken into consideration. According to that, adjustments in the product will be made.
Also, the results will be announced to the general public via media. | Also, the results will be announced to the general public via media.
Durability and transferability of main outputs | Durability and transferability of main outputs
The piloting (testing the product with actual users) will ensure that the results of the project are usable in real life situation. This will be promoted as a good example to the other regions in Europe. | The piloting (testing the product with actual users) will ensure that the results of the project are usable in real life situation. This will be promoted as a good example to the other regions in Europe.
The common ticket product will openly be used after the end of the project. Moreover, the partners will commit themselves to continue developing the common ticketing system, so that more products will be able on the market. | The interoperable ticket sale channels and payment options will openly be used after the end of the project. Moreover, the partners will commit themselves to continue developing the interoperability between ticketing systems, so that more options will be available on the market.
Activity A.T3.1 | Activity A.T3.1
Finding test users in Tallinn, Tartu and Helsinki (an open call via different media channels) | Finding test users in Tallinn, Tartu and Helsinki (an open call via different media channels)
Period: April - July 2020 | Period: March - June 2020
Deliverable D.T3.1.1: Test users, whose feedback will be analysed (200) | Deliverable D.T3.1.1: Test users for mobile apps, whose feedback will be analysed (200)
Deliverable D.T3.1.2: Test users for cards, whose feedback will be analysed (200)
Activity A.T3.2 | Activity A.T3.2
Testing - working closely with the selected test users (i.e. running A/B tests on ticket selling interface, collecting feedback on how the ticket product (cards) is working in the cities, what are the shortcomings etc.) | Testing - working closely with the selected test users (i.e. running A/B tests on ticket selling interface, collecting feedback on how the ticket product (on mobile) is working in the cities, what are the shortcomings etc.)
Perion: July - December 2020 | Period: June -September 2020
Deliverable D.T3.2.1: Report: lessons learnt | Testing - working closely with the selected test users (i.e. running A/B tests on ticket selling interface, collecting feedback on how the ticket product (on cards) is working in the cities, what are the shortcomings etc.)
Period: December 2020 - January 2021
Activity A.T3.3 | Deliverable D.T3.2.1: Report: lessons learnt (mobile)
Analysing feedback and making adjustments in the ticketing systems and ticket selling interface | Deliverable D.T3.2.2: Report: lessons learnt (cards)
Period: July 2020 - February 2021 | Activity A.T3.3
Deliverable D.T3.3.1: Adjusted ticketing systems in Tallinn, Tartu and Helsinki; adjusted ticket selling interface based on the analysed feedback (if necessary) (3) | Analysing feedback and making adjustments in the ticketing systems and ticket selling interface
Period: September 2020 - January 2021
Deliverable D.T3.3.1: Adjusted ticketing systems in Tallinn, Tartu and Helsinki; adjusted ticket selling interfaces based on the analysed feedback (if necessary) (3)
Activity A.T3.4
Internal working groups (3 meetings in total)
Period: February 2020 - January 2021
Deliverable D.T1.2.1: Meeting minutes, including testing principles (3)