{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Tööde graafik"],"not_rendered":{"charts":1,"images":1,"macros":1,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Tööde graafik","index":0,"n_rows":12,"n_cols":5,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
[]
[null,"Projekt","Algus","Kestvus","Lõpp"]
[null,"Vaksali Tuglase Kreutzwaldi projekteerimine","2018-11-11",180,{"$f":"Table13[[#This Row],[Column3]]+Table13[[#This Row],[Column2]]","v":"2019-05-10"}]
[null,"Topo-geodeetilised uuringud","2018-11-11",100,{"$f":"Table13[[#This Row],[Column3]]+Table13[[#This Row],[Column2]]","v":"2019-02-19"}]
[null,"Geoloogilised uuringud","2019-02-25",40,{"$f":"Table13[[#This Row],[Column2]]+Table13[[#This Row],[Column3]]","v":"2019-04-06"}]
[null,"Eskiisprojekti koostamine ja avalik arutelu","2018-11-11",125,"2019-02-28"]
[null,"Keskkonnamõjude eelhinnang","2019-03-14",30,{"$f":"Table13[[#This Row],[Column2]]+Table13[[#This Row],[Column3]]","v":"2019-04-13"}]
[null,"Dendroloogilised uuringud","2019-03-14",15,{"$f":"Table13[[#This Row],[Column2]]+Table13[[#This Row],[Column3]]","v":"2019-03-29"}]
[null,"Tänavavalgustuse projekteerimine","2019-03-21",45,"2019-04-01"]
[null,"Sademevee kanalisatsiooni projekteerimine","2019-03-21",{"$f":"Table13[[#This Row],[Column4]]-Table13[[#This Row],[Column2]]","v":25},"2019-04-15"]
[null,"Põhiprojekti koostamine sh maastikuarhitektuur",{"$f":"Table13[[#This Row],[Column4]]-Table13[[#This Row],[Column3]]","v":"2019-03-09"},60,"2019-05-08"]
[null,"Kooskõlastamine ",{"$f":"Table13[[#This Row],[Column4]]-Table13[[#This Row],[Column3]]","v":"2019-04-08"},30,"2019-05-08"]